## Planeacion equipo
Mes | Julio | Agosto | Septiembre | Octubre | Noviembre | Diciembre
Trabajador
Los Dioses
Gerson Nicolas Pineda Lara | 100%/0% | 90% / 10% | 90% / 10% | 100%/0% | 100%/0% | 100%/0%
Diego Andres Saavedra Perez | 100%/0% | 90% / 10% | 90% / 10% | 100%/0% | 100%/0% | 100%/0% | Impl. / Oper. | Ambos
Harold Abdullah Lamphrey Muñoz | 100%/0% | 100%/0% | 100%/0% | 100%/0% | 100%/0% | 100%/0%
Anomalías
Diana Patricia Aldana Moreno | 100%/0% | 50%/0 | 0 | 0 | 0 | 0
Medicamentos + Notificación
Kevin Camilo Rincon Bohorquez | 100%/0% | 100%/0% | 100%/0% | 100%/0% | 100%/0% | 0
Angela Maria Santos Hernandez | 100%/0% | 100%/0% | 100%/0% | 100%/0% | 100%/0% | 0
Cristian David Casas Diaz | 100%/0% | 0 | 0 | 0 | 0 | 0
Harold Burbano | 100%/0% | 0 | 0 | 0 | 0 | 0
Infraestructura
Daniel Castillo Giraldo | 100%/0% | 90% / 10% | 50% / 10% | 50% / 10% | 50% / 10% | 50% / 10%
Simon Calderon Lopez | 100%/0% | 80% / 20% | 10% / 50% | 10% / 50% | 10% / 50% | 10% / 50%
Jorge Humberto Sierra Laiton | 100%/0% | 50% / 50% | 10% / 50% | 10% / 50% | 10% / 50% | 10% / 50%
Javier Steven Barrera Toro | 100%/0% | 100%/0% | 0 | 0 | 0 | 0
Ricardo Sandoval | 100%/0% | 100%/0% | 0 | 0 | 0 | 0
Miguel Simbaqueba | 100%/0% | 100%/0% | 0 | 0 | 0 | 0
Evolución Fase II
Karen Julieth Diaz Cardozo | 100%/0% | 90% / 10% | 90% / 10% | 50% / 10% | 50% / 10% | 50% / 10%
Nicole Gabriela Gómez Higuera | 100%/0% | 100%/0% | 100%/0% | 0 | 0 | 0
Jessica Alejandra Rivera Garzon | 100%/0% | 100%/0% | 100%/0% | 0 | 0 | 0
Dispositivos médicos + Procedimientos No Quirurgicos
Manuel Alejandro Polo Gonzalez | 100%/0% | 100%/0% | 50% / 50% | 50% / 50% | 50% / 50% | 50% / 50%
Faider Camilo Trujillo Olaya | 100%/0% | 100%/0% | 0 | 0 | 0 | 0
Apoyos diagnóstico
Nicolas David Sanchez Yañez | 100%/0% | 100%/0% | 50% / 50% | 50% / 50% | 50% / 50% | 50% / 50%
Cristian Paul Angel Vahos | 100%/0% | 100%/0% | 50% / 50% | 50% / 50% | 50% / 50% | 50% / 50%
Tomas Carrillo Garcia | 100%/0% | 100%/0% | 0 | 0 | 0 | 0
SGA
Santiago Jose Garzon Lopez | 100%/0% | 70% / 30% | 70% / 30% | 70% / 30% | 30% / 70% | 30% / 70%
Johan David Espitia Pachon | 100%/0% | 70% / 30% | 70% / 30% | 70% / 30% | 30% / 70% | 30% / 70%
Franklin Julian Gonzalez Perez | 100%/0% | 70% / 30% | 70% / 30% | 70% / 30% | 30% / 70% | 30% / 70%
Valentina Villegas Correal | 100%/0% | 70% / 30% | 70% / 30% | 70% / 30% | 30% / 70% | 30% / 70%
Consultas, Estancias y Dashboard
Maryith Viviana Garzon Silva | 100%/0% | 100%/0% | 100%/0% | 100%/0% | 100%/0% | 0
Luis Antonio Zuluaga Ramirez | 100%/0% | 100%/0% | 100%/0% | 100%/0% | 100%/0% | 0
Daniel Santiago Avila Medina | 100%/0% | 100%/0% | 100%/0% | 0 | 0 | 0
Contratistas
Etelvina Mejía | 100%/0% | 100%/0% | 0%/100% | 0%/100% | 0%/100% | 0%/100%
Myriam Pulido | 100%/0% | 100%/0% | 100%/0% | 100%/0% | 100%/0% | 100%/0%
Claudia Quintero | 100%/0% | 100%/0% | 100%/0% | 100%/0% | 100%/0% | 100%/0%
Martha Ardila | 100%/0% | 100%/0% | 0%/100% | 0%/100% | 0%/100% | 0%/100%
Leonardo Beltrán | 100%/0% | 50% | 0 | 0 | 0 | N/A